# Payroll Standalone & Ecosystem — Features & Phases

Purpose: Break the payroll standalone initiative into three main features and their delivery phases, so each can become its own spec at the right time. Status: Planning document. No code changes. Grounded in the current codebase and the Phase 1 audit. Companion to: Phase1_Architecture_Audit.md, BusinessPortal_Payroll_Standalone_Product_KIRO_Handoff.md Date: 2026-09-13

This document maps the handoff direction (and the audit's R1-R7 roadmap) onto three concrete feature tracks. It records what exists today and what each phase must add. It does not claim anything is built beyond what the audit verified.

## Starting Point (verified in code)

- Payroll is a coherent domain in the [payroll] schema with its own services and controllers.

- Access is gated by a single flat payroll module key via ModuleAccessAttribute, seeded only against the Enterprise plan. There is no standalone entitlement and no capacity concept.

- Subscriptions use one [dbo].[Plan] row per tier, each carrying StripeProductId + StripePriceId, MonthlyPriceEur, AnnualPriceEur, MaxUsers, Slug. Checkout uses the plan's StripePriceId; webhooks reverse-map a Stripe price back to a plan.

- There is no Social Insurance export file, no Eurobank ISO 20022 XML, and no WorkforcePi ingestion contract.

## The Three Main Features (at a glance)

| # | Feature | Nature | Hard external dependency? |
| --- | --- | --- | --- |
| 1 | WorkforcePi integration (3 Inventors ecosystem) | Cross-product contract | Yes — WorkforcePi architecture |
| 2 | Individual Payroll product (gating, pricing, Stripe, capacity) | Commercial + platform | No — internal decision |
| 3 | Eurobank ISO 20022 document generation | Deterministic file export | Yes — authoritative Eurobank XSD (you will provide) |

Sequencing principle: Feature 2 is the foundational unblocker — Payroll cannot be sold standalone, and neither WorkforcePi-only nor Eurobank customers can be served commercially, until Payroll has an independent entitlement. Features 1 and 3 are largely independent of each other and can proceed in parallel once their external inputs are ready.

## Feature 1 — WorkforcePi Integration

Goal: Let approved workforce records flow natively from WorkforcePi into Payroll, without an artificial connector charge (handoff §11, §14, §15). WorkforcePi keeps owning rota/attendance/ reconciliation; Payroll keeps owning calculation onward.

Current state: Absent. Payroll accepts inputs via manual entry and EmployeeDefaultEarnings only.

Required contract characteristics (handoff §15): tenant-safe, idempotent, auditable, versionable, traceable to source, resistant to duplicate processing.

### Phases

- 1.1 — Contract definition (coordination). Agree the canonical PayrollWorkforceInput payload with the WorkforcePi architecture (period, regular/overtime worked time, paid/unpaid leave, approved adjustments, approval metadata, source reference). Versionable from day one. Blocked on WorkforcePi coordination.

- 1.2 — Ingestion endpoint + idempotency. Receive approved records, dedup by (tenant, employer, employee, period, source reference), store with source traceability. Reject/ ignore duplicates safely.

- 1.3 — Mapping into payroll inputs. Translate ingested worked-time into payslip earning lines (respecting existing EmployeeDefaultEarnings override rules), so batch generation can consume them.

- 1.4 — Reconciliation surface. Show which payroll inputs came from WorkforcePi vs manual, and let the user review before finalisation. No re-implementation of WorkforcePi's reconciliation engine (handoff guardrail §22).

- 1.5 — Native entitlement wiring. When both WorkforcePi and Payroll are subscribed, the integration is included — no separate connector SKU (handoff §14). Depends on Feature 2 entitlement.

Guardrails: do not duplicate attendance/reconciliation; do not make WorkforcePi mandatory for Payroll; do not charge separately for the native path by default.

## Feature 2 — Individual Payroll Product

Goal: Make Payroll independently sellable — its own entitlement, its own capacity-banded pricing, its own Stripe products — while remaining includable in Enterprise (handoff §16-§18).

This feature has four sub-tracks, matching the request.

### 2.1 — Payroll gating (entitlement decoupling) — audit R1

Current state: payroll key is Enterprise-only; ModuleAccessAttribute layer 4 blocks anyone without it.

- 2.1.a Decision: how is standalone Payroll represented? It must be purchasable without the full Portal, so the current "add-on requires Enterprise" pattern (Inventory Intelligence) does not fit. Likely a first-class Payroll subscription that can coexist with, or be independent of, a Portal tier.

- 2.1.b Entitlement source: change only what populates IncludedModules so payroll can be granted via its own entitlement. Keep the payroll key and the 5-layer filter intact.

- 2.1.c Preserve Enterprise inclusion: Enterprise-includes-Payroll remains valid (handoff §17 says do not force removal). Both paths must resolve to the same access decision.

- 2.1.d Standalone navigation/shell: a Payroll-only customer needs a coherent entry point that does not assume the full Portal chrome is present.

### 2.2 — Payroll product pricing (capacity bands) — audit R2

Current state: No capacity concept anywhere in code.

- 2.2.a Capacity model: introduce employee-capacity bands (1-25, 26-100, 101-250, 251+ custom) on the Payroll entitlement.

- 2.2.b Non-destructive enforcement: when active-employee count exceeds the licensed band, trigger an upgrade/administrative flow — never delete or damage payroll data (handoff §18).

- 2.2.c Configurable prices: all band prices live in data, never in payroll calculation/domain logic (handoff §4). Support the "pay for 10 months, get 12" annual model already used platform-wide.

- 2.2.d Capacity counting rule: define precisely what counts toward a band (e.g. active employees in the current period) and where it is evaluated.

### 2.3 — Payroll Stripe update (new products per Payroll tier) — extends audit R2

Current state: One Plan row per tier with a single StripeProductId/StripePriceId; checkout and webhooks are plan-price based.

- 2.3.a New Stripe products/prices: one Stripe product per Payroll capacity band, each with monthly and annual prices. Store StripeProductId/StripePriceId per band (new plan rows or a new Payroll-plan table — decision in 2.1.a).

- 2.3.b Checkout path: extend CheckoutService so a Payroll-band purchase resolves the correct band price. Reuse the existing subscription-mode session pattern and tax-rate handling.

- 2.3.c Webhook mapping: extend the price->plan reverse lookup (GetPlanByStripePriceIdAsync) so Payroll-band prices resolve to the Payroll entitlement + band.

- 2.3.d Band changes: handle upgrade/downgrade between bands (proration, effective date) through Stripe subscription updates, keeping capacity enforcement (2.2.b) in sync.

### 2.4 — Something else (open items to confirm)

Candidates that belong to "making Payroll a product," to be confirmed with you:

- P&L / Compliance as optional capabilities (audit R3): guard PayrollPnlService and ComplianceIntegrationService behind "is the Portal module subscribed?" so Payroll runs cleanly standalone (no-op integration) and richly inside Portal.

- Country mapping de-risk (audit R4): move the hard-coded country name->ISO map out of PayslipCalculationOrchestrator into data, and replace the silent "CY" fallback with an explicit fail-closed validation error.

- Payroll-only onboarding/trial: how a Payroll-only prospect signs up, trials, and is billed.

- Migration: how existing Enterprise-with-Payroll customers map onto the new model without disruption.

Tell me which of these (or others) you want folded into "2.4" and I will scope them.

## Feature 3 — Eurobank ISO 20022 Document

Goal: Generate a valid, deterministic Eurobank-compatible ISO 20022 payment file (pain.001.001.03 or .09) that the customer uploads to Eurobank Online Banking Business. 3 Inventors generates the file only — never authenticates, authorises, or executes the payment (handoff §9).

Current state: Absent. You will provide the Eurobank documentation/XSD.

### Phases

- 3.1 — Specification intake (blocked until docs provided). Confirm the exact ISO 20022 version, the authoritative XSD, and Eurobank's implementation guidelines. Choose one version to implement fully rather than promising both (handoff §9.3).

- 3.2 — Deterministic generator. Map a finalised payroll run to Group Header -> Payment Information -> Transaction Information: message id, creation timestamp, transaction count, control sum, debtor IBAN, per-employee creditor + amount + end-to-end id + remittance info.

- 3.3 — Validation. Schema-validate against the XSD; verify transaction count and control sum; enforce unique message identifiers; produce clear failure messages.

- 3.4 — Export + audit record. Downloadable XML plus a payment-file audit record (GeneratedBy, GeneratedAt, PayrollPeriod, PayrollRunId, TransactionCount, ControlTotal, Format, FormatVersion, FileIdentifier) so any file traces back to a finalised run (handoff §19).

- 3.5 — Commercial inclusion. Once validated, treat standard Eurobank XML export as a Payroll capability, not a separate recurring connector fee (handoff §10).

Guardrails: never call it a bank API; never store banking credentials; do not build production XML from the sample — validate against the authoritative XSD.

## Cross-Feature Dependency Map

Feature 2.1 (gating) ── unblocks ──> Feature 2.2 (bands) ──> Feature 2.3 (Stripe)

│                                                         │

└── unblocks ──> Feature 1.5 (native WFPi entitlement)    │

│

Feature 1.1-1.4 (WorkforcePi contract) ── parallel, needs WFPi coordination

Feature 3.1-3.4 (Eurobank XML) ── parallel, needs Eurobank XSD (you provide)

Recommended order:

- Feature 2.1 (Payroll gating) — resolves the one active guardrail violation from the audit.

- Feature 2.2 + 2.3 (bands + Stripe) — commercially inseparable from gating.

- In parallel, start Feature 3 spec intake as soon as you hand over the Eurobank documentation.

- Feature 1 once WorkforcePi contract coordination is scheduled.

## What I Need From You

- Feature 2.1.a decision: is standalone Payroll a first-class subscription independent of Portal tiers, or something else? (This shapes 2.2 and 2.3.)

- Feature 2.4 scope: which open items to include.

- Feature 3: the Eurobank documentation/XSD and the target ISO 20022 version.

- Feature 1: confirmation of when WorkforcePi contract coordination can happen.

Once you confirm the 2.1.a direction, the natural first spec is Feature 2.1 — Payroll gating.